{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Configure","Instructions","GoCHAMPION project evaluation","Summary"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Configure","index":0,"n_rows":20,"n_cols":5,"rows_kept":20,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
["Choose questions for the questionnaire. You can add your own questions by writing them to the first free row after table. "]
["<Mandatory>"]
["Use question","CRITERIA","Poor","Adequate","Good"]
["YES","Business case","The project is not aligned with the long-term strategy of any companies involved and does not have a solid business case.","The project is aligned with the long-term strategy of the involved companies or has a solid business case.","The project is aligned with the long-term strategy of the companies involved and has a solid business case. Co-operation is meaningful for all companies."]
["NO","Window of opportunity","There is no clear window of opportunity in the company's portfolio for the product/service.","The window of opportunity for the product/service is not clear but it can be justified.","There is a clear window of opportunity in the company's portfolio for the product/service."]
["NO","Plans & resources","Company-level project and resource plans are available.","Partners' project and resource plans are available.","We have approved/confirmed project and resource plans for our company that also include partners’ plans."]
["YES","Project manager","The project manager lacks 3–4 qualities of available time, motivation, competencies, ability to influence, and credibility in organisation.","The project manager lacks 1–2 qualities of available time, motivation, competencies, ability to influence, and credibility in the organisation.","The project manager has time available, motivation, competencies, ability to influence, and credibility in the organisation."]
["YES","Schedule alignment","We have no visibility of our partners' schedules.","Partners' schedules are available but they are not synchronised at a project level or the schedules are conflicting with the project schedule.","Partners' schedules are aligned with project schedules."]
["YES","Capacity & investments","Project execution requires additional investments or causes delays in some other project, OR the project decreases partners’ business opportunities, OR we have doubts regarding partners' capacity.","A successful project is possible if work effort or investment estimates do not change.","A project does not require additional investments and does not cause unreasonable risk for the partners. There is a high success probability, even though additional work effort or investments are needed."]
["YES","Contracts","We have not worked with the partners before, even at the company level. Legal agreements enabling co-operation do not exist.","The company has worked with the partners before but legal agreements need to be updated for this project.","We have worked with the partners before and the legal agreements are still valid."]
["YES","Division of power","We have not agreed with partners who make decisions and upon what. It is not possible to make decisions in a reasonable time.","Power division with the partners has been carried out but decision-making is too slow.","All companies involved know who makes decisions and what is decided upon. Decision-making is rapid."]
["YES","Competencies","Competence needs for the projects are known but suitable personnel are not available.","We have all the critical competencies in the project but some of the key personnel are newcomers.","We have all the critical competencies in the project and everyone is familiar with the project and the companies involved."]
["YES","Division of work","We have not agreed on work division with the partners.","Work division with partners has been agreed but it is not documented.","We have clearly agreed work division with partners to avoid overlapping tasks and grey areas."]
["YES","Co-operation history","We have not worked with the partners before, OR previous co-operation with the partners was not successful.","We have worked successfully with the partners before as a company but the project personnel have no personal experience.","Project personnel have successfully worked with the partners on previous projects."]
["YES","Work practices","We have not worked with the partners before. Work practices and processes for co-operation do not exist.","The company has worked with the partners before but work practices and processes need to be updated for this project.","We have worked with the partners before and agreed work practices and processes are still valid."]
["YES","(ICT) tools","We have not worked with the partners before. (ICT) tools for co-operation do not exist.","The company has worked with the partners before but the (ICT) tools used are not applicable for this project.","We have worked with the partners before and the (ICT) tools used are still valid."]
["YES","Maturity of technology","The selected technological solution is being used for the first time in the company. The solution has not been used in other companies.","The selected technological solution is being used for the first time in the company. The solution has already been used in another company.","The selected technological solution has already been verified and used in our other products/services."]

{"sheet":"Instructions","index":1,"n_rows":8,"n_cols":3,"rows_kept":8,"cut":false,"hidden":false,"merged":[]}
[]
["GoCHAMPION project evaluation worksheet"]
["Criteria",null,"Project evaluation criteria are listed in this column. The fill color on each criteria will be automatically updated based on the selected status."]
["Status options",null,"Each criteria has three status options. Descriptions for each status options is given separately for each criteria."]
[null,"Poor","Usually \"poor\" means that the topic is not properly taken care of in the project."]
[null,"Adequate","\"Adequate\" refers to situation where some actions have been taken but something more needs to be done"]
[null,"Good","\"Good\" status means that all needed actions have been taken to ensure project success."]
["Comments",null,"Description of the status per each evaluation criteria. Also, possible actions should be mentioned here."]

{"sheet":"GoCHAMPION project evaluation","index":2,"n_rows":14,"n_cols":6,"rows_kept":14,"cut":false,"hidden":false,"merged":[[0,0,1,0],[0,1,0,3],[0,5,1,5]]}
["CRITERIA","STATUS",null,null,"Evaluation","Comments"]
[null,"Poor","Adequate","Good","24.3.2016"]
["Business case","The project is not aligned with the long-term strategy of any companies involved and does not have a solid business case.","The project is aligned with the long-term strategy of the involved companies or has a solid business case.","The project is aligned with the long-term strategy of the companies involved and has a solid business case. Co-operation is meaningful for all companies."]
["Project manager","The project manager lacks 3–4 qualities of available time, motivation, competencies, ability to influence, and credibility in organisation.","The project manager lacks 1–2 qualities of available time, motivation, competencies, ability to influence, and credibility in the organisation.","The project manager has time available, motivation, competencies, ability to influence, and credibility in the organisation."]
["Schedule alignment","We have no visibility of our partners' schedules.","Partners' schedules are available but they are not synchronised at a project level or the schedules are conflicting with the project schedule.","Partners' schedules are aligned with project schedules."]
["Capacity & investments","Project execution requires additional investments or causes delays in some other project, OR the project decreases partners’ business opportunities, OR we have doubts regarding partners' capacity.","A successful project is possible if work effort or investment estimates do not change.","A project does not require additional investments and does not cause unreasonable risk for the partners. There is a high success probability, even though additional work effort or investments are needed."]
["Contracts","We have not worked with the partners before, even at the company level. Legal agreements enabling co-operation do not exist.","The company has worked with the partners before but legal agreements need to be updated for this project.","We have worked with the partners before and the legal agreements are still valid."]
["Division of power","We have not agreed with partners who make decisions and upon what. It is not possible to make decisions in a reasonable time.","Power division with the partners has been carried out but decision-making is too slow.","All companies involved know who makes decisions and what is decided upon. Decision-making is rapid."]
["Competencies","Competence needs for the projects are known but suitable personnel are not available.","We have all the critical competencies in the project but some of the key personnel are newcomers.","We have all the critical competencies in the project and everyone is familiar with the project and the companies involved."]
["Division of work","We have not agreed on work division with the partners.","Work division with partners has been agreed but it is not documented.","We have clearly agreed work division with partners to avoid overlapping tasks and grey areas."]
["Co-operation history","We have not worked with the partners before, OR previous co-operation with the partners was not successful.","We have worked successfully with the partners before as a company but the project personnel have no personal experience.","Project personnel have successfully worked with the partners on previous projects."]
["Work practices","We have not worked with the partners before. Work practices and processes for co-operation do not exist.","The company has worked with the partners before but work practices and processes need to be updated for this project.","We have worked with the partners before and agreed work practices and processes are still valid."]
["(ICT) tools","We have not worked with the partners before. (ICT) tools for co-operation do not exist.","The company has worked with the partners before but the (ICT) tools used are not applicable for this project.","We have worked with the partners before and the (ICT) tools used are still valid."]
["Maturity of technology","The selected technological solution is being used for the first time in the company. The solution has not been used in other companies.","The selected technological solution is being used for the first time in the company. The solution has already been used in another company.","The selected technological solution has already been verified and used in our other products/services."]

{"sheet":"Summary","index":3,"n_rows":14,"n_cols":1,"rows_kept":14,"cut":false,"hidden":false,"merged":[]}
["Summary"]
["CRITERIA"]
["Business case"]
["Project manager"]
["Schedule alignment"]
["Capacity & investments"]
["Contracts"]
["Division of power"]
["Competencies"]
["Division of work"]
["Co-operation history"]
["Work practices"]
["(ICT) tools"]
["Maturity of technology"]